## Data
Risk Source | Risk code | Risk | Potential Consequence | Risk probability | Risk Impact | Risk Rating | Potential Mitigation
1. Climate
| CL01 | Strong winds caused by tropical cyclones or low pressure systems. | Injury or death, destruction/damage to buildings and infrastructure. | Possible | Major | High | >Building and infrastructure designed to withstand extreme weather. >Design category for cyclone rating and breakwaters and land masses designed for Q100 event. >Construction Phase Disaster Action Plan includes early warnings for evacuation of personnel and equipment.
| CL02 | Flooding caused by storm surge. | Destruction/damage to buildings and infrastructure. | Possible | Major | High | Building and infrastructure designed to withstand extreme weather. Design category for cyclone rating and breakwaters and land masses designed for Q100 event. Construction Phase Disaster Action Plan |  | Risk Rating Table
| CL03 | Flooding caused by heavy rainfall. | Destruction/damage to buildings and infrastructure. | Possible | Major | High | Building and infrastructure designed to withstand extreme weather. Design category for cyclone rating and breakwaters and land masses designed for Q100 event. Construction Phase Disaster Action Plan |  | Impact
| CL04 | Extended wet weather during construction. | Construction programme delays. | Possible | Major | High | Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event | Probaibility | Insignificant | Minor | Moderate | Major | Catastrophic
2. Land | [7 empty] | Almost Certain | Moderate | High | Extreme | Extreme | Extreme
| LA01 | Degradation of water quality due to erosion. | Degradation of water quality due to erosion. | Possible | Minor | Low | Site fully bunded and contained. Sedimentation and erosion control measures in place under EMP | Likely | Low | Moderate | High | Extreme | Extreme
| LA02 | Unstable slopes and structures due to soil instability. | Destruction/damage to buildings and infrastructure. | Possible | Moderate | Moderate | Geotechnical Analysis for design of slopes and batters. Specific design parameters for retaining and revetment works. | Possible | Negligible | Low | Moderate | High | Extreme
| LA03 | Degradation of water quality due to existing contaminants in sediment. | Degradation of water quality. | Possible | Moderate | Moderate | Site fully bunded and contained. Sedimentation and turbidity control measures in place under EMP. | Unlikely | Negligible | Negligible | Low | Moderate | High
| LA04 | Acidification of water due to acid sulphate soils. | Degradation of water quality. | Rare | Moderate | Negligible | Site fully bunded and contained. Sedimentation, turbidity control and treatment measures in place under EMP. | Rare | Negligible | Negligible | Negligible | Low | Moderate
| LA05 | Collapse of new revetment walls during construction stage. | Damage to equipment, risk to personnel, construction delays | Unlikely | Moderate | Low | Level 1 construction supervision - appropriate design based on investigation and analysis
| LA06 | Failure of depressurization system through sand layers while excavating canals | Sudden instability with destruction/ damage to infrastructure and equipment and risk to personnel | Rare | Moderate | Negligible | Monitoring of depressurization system through construction as identified in EMP
| LA07 | Potential high seepage rates through existing southern revetment wall | Additional pumping requirements | Unlikely | Moderate | Low | Additional depressurization wells along southern revetment wall
| LA08 | Slow consolidation of stockpiled organic soft clay in parkland area | Short-term consolidation of reclaimed parklands | Possible | Moderate | Moderate | Monitoring of settlement rates additional surcharge/wick drains, minor remediation grading works.
| LA09 | Difficulty in compaction of fill | Construction staging method delays / site trafficability issues, increased resultant settlements / instability | Rare | Moderate | Negligible | Level 1 construction supervision - appropriate placement compaction methods
| LA10 | Shallow sand beds not identified during site investigation | Higher seepage rates, instability | Rare | Moderate | Negligible | Monitoring during construction stage. Construction of additional extraction wells as required
| LA11 | Poor installation of HDPE/Bentonite liner in breakwaters and bunds | Increased seepage rates/ erosion of breakwaters and bunds | Possible | Moderate | Moderate | Close construction stage control of HDPE / Bentonite placement. Additional dewatering wells
| LA12 | Puncture of HDPE/Bentonite liner | Increased seepage rates/ erosion of breakwaters and bunds | Likely | Minor | Moderate | Close construction stage control of HDPE / Bentonite placement over sand bedding. Additional dewatering wells.
| LA13 | Under estimated modelling assumptions for seepage | Higher pumping requirements | Unlikely | Moderate | low | Monitoring during construction stage, construction of additional extraction wells as required.
| LA14 | Inability to move / handle organic soft clay material | Construction staging method delays | Possible | Major | High | Undertake trials of equipment and handling techniques proposed by contractor.
| LA15 | Imported select fill not suitable to purpose | Construction staging method delays, material performance issues | Possible | Moderate | Moderate | Level 1 supervision of imported fill. Additional investigation and testing of source material for suitability.
| LA16 | Large rock fill for access construction road fails to penetrate fully through organic soft clay | Localized and potentially abrupt settlements of surface | Possible | Major | High | Level 1 supervision of construction methodology.
| LA17 | Abutment instability of temporary Ross Creek bridge | Temporary closure of haul route and material access to site | Possible | Major | High | Geotechnical investigation and analysis of abutments and appropriate design.
| LA18 | Poor water quality in basin upon rewatering of site | Turbidity issues | Likely | Moderate | High | Controlled, low velocity rewatering of site, monitor turbidity, open areas progressively cell by cell.
| LA19 | Inexperienced earthworks contractor | Time delays | Unlikely | Major | Moderate | Selection of experienced contractor with experiencedpersonnel on site.
3. Traffic and Transport
| TT01 | Accidental spill from material transfer | Destruction/damage to environment from material spill | Rare | Insignificant | Negligible | Material spill and erosion control measures in place under EMP.
| TT02 | Traffic incidents with existing Road Users | Injury to existing road user | Unlikely | Major | Moderate | Haul routes and Site Traffic Management Plan.
| TT03 | Degradation of traffic and transport infrastructure | Increased road noise | Likely | Moderate | High | Haul routes and Site Traffic Management Plan.
| TT04 | Degradation of traffic and transport infrastructure | Damage to infrastructure | Possible | Moderate | Moderate | Remediation or repair to damaged infrastructure
| TT05 | Increased site traffic impeding public access | Reduced existing access for pedestrians and cyclists | Possible | Minor | Low | Short term impact. Selection of haul routes to minimise impacts.
4. Non-transport infrastructure
| IN01 | Power supply insufficient, infrastructure upgrade required. | Power supply insufficient, infrastructure upgrade required. | Rare | Insignificant | Negligible | Design loadings calculated and liaison with authorities to provide sufficient lead times for upgrades
| IN02 | Telecom service insufficient, infrastructure upgrade required | Telecom service insufficient, infrastructure upgrade required. | Rare | Insignificant | Negligible | Design loadings calculated and liaison with authorities to provide sufficient lead times for upgrades
| IN03 | Infrastructure upgrade required | Infrastructure upgrade required. | Unlikely | Moderate | Low | Design loadings calculated and sufficient capacity included in design (water, sewerage).
| IN04 | Damage to infrastructure | Degradation of water quality | Unlikely | Moderate | Low | Stormwater management in accordance with project SWMP.
5. Waste
| WA01 | Excessive material and services resources use during construction. | Depletion of natural resources. | Possible | Moderate | Moderate | Waste reduction and recycling in accordance with the waste hierarchy in the EPP Waste.
| WA02 | Emission of liquid wastes to waterways due to poor practices in waste containment, waste transport and stormwater control. | Deterioration of water quality and ecological values in aquatic ecosystems. | Possible | Major | High | Stormwater management in accordance with project SWMP, hazardous materials management in accordance with project EMP, waste minimisation and management in accordance with the project EMP.
| WA03 | Emission of solid wastes to land due to poor practices in waste containment, waste transport and stormwater control. | Recreational and amenity impacts. | Possible | Moderate | Moderate | Waste minimisation and management practices for storage and disposal of solid waste in accordance with the project SWMP and EMP.
| WA04 | Emission of dust and particulates to air due to poor construction practices. | Human health and amenity impacts. | Possible | Moderate | Moderate | Air quality control measures during construction in accordance with the project EMP.
6. Water Resources
| WR01 | Release of turbid waters during site dewatering. | Impacts on seagrasses and ecological communities in Cleveland Bay | Likely | Moderate | High | Control of dewatering under the EMP, three indicative discharge areas are highlighted adjacent to each of the breakwaters. Preferred locations in rank order are discharge to Ross Creek, discharge adjacent to northern breakwater, discharge adjacent Strand breakwater.
7. Coastal Resources
| CE01 | Extreme Storm Tide Event - to 100 year ARI. | Destruction/damage to equipment and infrastructure. | Possible | Minor | Low | The 100 year ARI is the Designated Storm Tide Event (as defined by EPA). Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event.
| CE02 | Extreme Storm Tide Event - greater than 100 year ARI. | Destruction/damage to equipment and infrastructure. | Rare | Catastrophic | Moderate | The 100 year ARI is the Designated Storm Tide Event (as defined by EPA). Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event.
| CE03 | Extreme Waves - to 100 year ARI. | Destruction/damage to equipment and infrastructure. | Possible | Minor | Low | Marine infrastructure structurally designed to accommodate 100 year ARI cyclone waves with minimal damage. Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event.
| CE04 | Extreme Waves - greater than 100 year ARI. | Destruction/damage to equipment and infrastructure. | Rare | Catastrophic | Moderate | Marine infrastructure structurally designed to accommodate 100 year ARI cyclone waves with minimal damage. Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event.
| CE05 | Breakwater failure. | Destruction/damage to equipment and infrastructure. | Rare | Major | Low | Marine infrastructure structurally designed to accommodate 100 year ARI cyclone waves with minimal damage. Site secured and site personnel and equipment relocated to safe refuge. Site remediation works post event.
8. Air
| AI01 | Emission of dust and particulate matter from construction activities. | Amenity impacts on existing residents in the vicinity of the project site. | Possible | Moderate | Moderate | Air quality control measures in accordance with the project EMP.
8. Visual Amenity and Lighting
VL01
9. Noise and Vibration
| NV01 | Construction noise impact on existing residential and retail areas. | Annoyance, resident complaints | Possible | Moderate | Moderate | Establish complaint hotline, preparation of construction noise and vibration management plan, execution of noise and vibration management and minimisation
| NV02 | Increase in road traffic noise at residences along public roads during construction. | Annoyance, resident complaints, Council/DMR may refuse permission to use proposed haulage routes due to unreasonable noise levels. | Possible | Moderate | Moderate | Establish complaint hotline, select haul routes with minimum number of properties affected, maintain and operate equipment efficiently
| NV03 | Noise from construction impacts on marine life. | Physical and behavioural impacts on mammals in vicinity of project site. | Possible | Major | High | Visual survey of site to detect noise sensitive species prior to commencement of construction works. Dispersal of noise sensitive species using motorised vessel.
| NV04 | Vibration impact from construction equipment on existing residences. | Human discomfort, complaints to Council. | Unlikely | Moderate | Low | Establish complaint hotline, minimise duration of impacting works.
| NV05 | Vibration impact from construction equipment on existing residences. | Structural damage to nearby buildings. | Unlikely | Major | Moderate | Carry out dilapidation report. Establish complaint hotline. Minimise duration of impacting works.
| NV06 | Vibration impact from construction equipment on Casino and Entertainment Centre | Human discomfort, complaints to Council. | Possible | Moderate | Moderate | Establish complaint hotline, preparation of construction noise and vibration management plan, vibration monitoring.
| NV07 | Vibration impact from construction equipment on Casino and Entertainment Centre | Structural damage to nearby buildings. | Possible | Major | High | Carry out dilapidation report. Establish complaint hotline, preparation of construction noise and vibration management plan, vibration monitoring.
10. Nature Conservation
| NC01 | Sediment destabilisation through changes in sediment transport regime (e.g. dredging in adjacent areas). | Seagrass impacts | Likely | Major | Extreme | Use of silt curtains during dredging and dredge protocols contained in project EMP.
| NC02 | Light attenuation through, for example, increased turbidity associated with dredging activities. | Seagrass impacts | Possible | Major | High | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC03 | Nutrient enrichment leading to increased macroalgal growth (e.g. effluent discharge). | Seagrass impacts | Unlikely | Major | Moderate | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC04 | Contamination from spill (oil, chemicals). | Seagrass impacts | Possible | Major | high | Spill contingency procedures contained in project EMP. Controlled via fully bunded site.
| NC05 | Contamination from disturbed contaminated sediments. | Seagrass impacts | Unlikely | Major | Moderate | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC06 | Noise pollution (impact on organisms relying on seagrass beds). | Seagrass impacts | Almost Certain | Major | Extreme | Visual survey of site to detect noise sensitive species prior to commencement of construction works. Dispersal of noise sensitive species using motorised vessel.
| NC07 | Smothering through garbage and debris accumulation. | Seagrass impacts | Unlikely | Major | Moderate | Waste control measures contained in project EMP. Waste controlled via fully bunded site.
| NC08 | Light attenuation through turbidity. | Coral reef impacts | Possible | Major | high | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC09 | Sediment deposition. | Coral reef impacts | Possible | Major | high | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC10 | Nutrient enrichment leading to increased macroalgal growth. | Coral reef impacts | Unlikely | Major | Moderate | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC11 | Contamination and mortality from spill (oil,chemicals). | Coral reef impacts | Possible | Major | High | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC12 | Contamination from disturbed contaminated sediments. | Coral reef impacts | Unlikely | Major | Moderate | Use of silt curtains during dredging and dredge protocols contained in project EMP. Controlled dewatering of fully bunded site.
| NC13 | Smothering through garbage and debrisaccumulation. | Coral reef impacts | Unlikely | Moderate | Low | Waste control measures contained in project EMP. Waste controlled via fully bunded site.
11. Cultural Heritage
| CH01 | Negative impacts on Aboriginal cultural values. | Diminished cultural significance of Cleveland Bay and local waterways. | Unlikely | Moderate | Low | Cultural monitoring and site inspection program to be implemented during development of the site. Training of construction contractors and staff.
| CH02 | Disturbance of sites that may remain in sub-tidal deposits. | Negative impact on archaeological record. | Unlikely | Moderate | Low | Implementation of a protocol in the event of a find of cultural significance and appropriate management actions in consultation with the Traditional Owners.
| CH03 | Negative impacts on local environmental values. | Diminished Aboriginal use of the area for cultural practices such as fishing and foraging. | Unlikely | Moderate | Low | Review of expert environmental reports by Traditional Owners.
12. Social
| SO01 | Air quality impacts during construction. | Adverse impacts on amenity and liveability | Possible | Major | High | Air quality control measures in accordance with the project EMP.
| SO02 | Noise impacts during construction. | Adverse impacts on amenity and liveability | Possible | Major | High | Establish complaint hotline, preparation of construction noise and vibration management plan, execution of noise and vibration management and minimisation.
| SO03 | Increased marine traffic. | Impacts on existing recreational uses. | Rare | Insignificant | Negligible | Planned barge movements provided to TPA and harbour master.
| SO04 | Increased vehicular traffic. | Impacts on existing and future residents. | Possible | Moderate | Moderate | Provide density plans as part of EIS submission to enable government authorities to plan for service upgrades with maximum lead times.
| SO05 | Reduced public amenity during construction. | Construction related activities will generate some amenity impacts on the Strand thereby reducing amenity for users. | Likely | Minor | Moderate | Short term impact. Selection of haul routes to minimise impacts.
| SO06 | Reduced public access to recreational space and facilities during construction. | Inability of previous users to access old breakwater (e.g. recreational anglers). | Almost Certain | Minor | High | Safety considerations must come to the fore during construction and public access to the breakwater would be inappropriate.
| SO07 | Environmental degradation. | Degradation of the marine environment in particular during construction | Unlikely | Major | Moderate | Adhesion to environmental protocols contained in project EMP. Controlled impacts via fully bunded site.
| SO08 | Increased dust, noise and congestion along haulage routes. | Residential and road user disamenties resulting from sustained periods of quarry materials haulage. | Possible | Moderate | Moderate | Short term impact. Selection of haul routes to minimise impacts.
13. Health an Safety
| HS01 | Construction traffic. | Increased traffic on haul roads and noise nuisance impacts on existing businesses, schools and residences. | Likely | Moderate | High | Establish complaint hotline, select haul routes with minimum number of properties affected, maintain and operate equipment efficiently.
| HS02 | Public health and safety. | Impacts on public H&S during construction. | Unlikely | Major | Moderate | Adequate signage and fencing to secure the site and prevent unauthorised access.
| HS03 | Construction health and safety. | Health and Safety impacts on construction workforce. | Unlikely | Major | Moderate | Construction contractor to implement WH&S measures.
14. Economy
| EC01 | Potential impact on existing labour markets. | Inability of existing workforce to provide adequate skills and labour. | Unlikely | Moderate | Low | Encouragement of suitable labour force into local market.
| EC02 | Potential impacts on existing housing and accommodation stock (during construction). | Inability of existing accommodation to cope with increased demand. | Possible | Moderate | Moderate | Expected labour force will be drawn from existing local workforce.
| EC03 | Potential impact on future regional development resulting from use of significant quantities of quarry materials. | Inability of future projects to source sufficient volumes of quarry materials from local sources (resulting in increased costs and project delays) | Rare | Moderate | Negligible | Roseneath Quarry has been specifically re-opened to supply materials for this project. Significant reserves still exist in the vicinity to provide material for future developments
| EC04 | Potential impact on existing marine users during construction. | Impairment of operations of existing Ross Creek users. | Rare | Minor | Negligible | "Ensure production schedules are consistent with existing user requirements.
16. Construction Methodology
| CM01 | Sand Lenses Slip Failure. | Destruction of Property | Possible | Moderate | Moderate | Geotechnical Analysis for design of slopes and batters. Specific design parameters for retaining and revetment works. Level 1 construction supervision.
| CM02 | Percolation and Dewatering. | Work Site Flooding | Likely | Moderate | High | Monitoring of depressurization system through construction as identified in EMP. Reduced WorkingCells.
| CM03 | Dewatering Equipment Failure. | Work Site Flooding | Rare | Moderate | Negligible | Level 1 construction supervision. Reduced Working Cells.
| CM04 | HDPE / Bentonite Membrane Failure. | Work Site Flooding | Likely | Moderate | High | Monitoring of depressurization system through construction as identified in EMP. Reduced Working Cells.
| CM05 | Wonky Holes. | Work Site Flooding | Possible | Moderate | Moderate | Monitoring of depressurization system through construction as identified in EMP. Reduced Working Cells.
| CM06 | Spoil Disposal unsuitable as fill material. | Movement of Materials Off Site and Treatment. | Almost Certain | Minor | High | Agreement with Port Authority to receive materials to enable relocation and treatment.
| CM07 | Parklands Settlement. | Destruction of Property (landscape element) | Almost Certain | Minor | High | Site remediation works post event.
| CM08 | Green Topped Breakwaters. | Destruction of Property | Possible | Moderate | Moderate | Marine infrastructure structurally designed to accommodate 100 year ARI cyclone waves with minimal damage. Site secured and site personnel and equipment relocated to safe refuge. Site remediationworks post event.
| CM09 | Green Topped Seawall. | Destruction of Property (landscape element) | Possible | Minor | Low | Marine infrastructure structurally designed to accommodate 101 year ARI cyclone waves with minimal damage. Site secured and site personnel and equipment relocated to safe refuge. Site remediationworks post event.
| CM10 | Sheet Pile Failure. | Destruction of Property | Unlikely | Moderate | Low | Site fully bunded post sheet pile installation. Site remediation works post event.
| CM11 | Loss of Construction Equipment. | Destruction / Loss of Equipment Property | Rare | Insignificant | Negligible | Construction contractor to implement WH&S measures. Site remediation works post event.
| CM12 | Construction Equipment Failure. | Destruction / Loss of Equipment Property | Unlikely | Insignificant | Negligible | Site remediation works post event.
| CM13 | Construction WH&S Risks. | Injury or Loss of Life | Possible | Major | High | Construction contractor to implement WH&Smeasures.

## Schema and RisKG
[8 empty] | Figure 3 | Risk Knowledge graph (RisKG) for the Terminal project
RisKG ontology model (DB schema)
Table 1
| S/N | Entity | Number
| 1 | Project | 1
| 2 | Risk source | 15
| 3 | Risk | 94
| 4 | Risk rating | 94
| 5 | Risk consequence | 94
| 6 | Risk mitigation | 94
|  | Total | 392
Table 2
| S/N | Relationship type | Number
| 1 | hasRiskSource | 15
| 2 | hasRisk | 94
| 3 | hasRiskRating | 94
| 4 | hasRiskConsequence | 94
| 5 | highRiskMitigation | 94
|  | Total | 391
|  |  |  | Category | Entity or relationship type | Number | Total
|  |  |  | Entity | Project | 1
[5 empty] | Risk source | 15
[5 empty] | Risk | 94
[5 empty] | Risk rating | 94
[5 empty] | Risk consequence | 94
[5 empty] | Risk mitigation | 94 | 392
|  |  |  | Relationship | hasRiskSource | 15
[5 empty] | hasRisk | 94
[5 empty] | hasRiskRating | 94
[5 empty] | hasRiskConsequence | 94
[5 empty] | highRiskMitigation | 94 | 391

## Query code for the used cases
S/N | Use Cases | Query Code
1 | To identify all the risk sources of the project | >> MATCH(a:PROJECTNAME)-[:hasRiskSource]-> (b:RISKSOURCE) RETURN b.Name AS RiskCategory For Visualization >> MATCH(a:PROJECTNAME)-[:hasRiskSource]-> (b:RISKSOURCE) RETURN a, b
2 | To identify the risks under a specific risk source (e.g Health and Safety Risks). | >> MATCH(a:PROJECTNAME)-[:hasRiskSource]-> (b:RISKSOURCE {Name:"Health and Safety"})-[:hasRisk]->(c:RISK) RETURN c.Name AS RiskCode, c.Description AS Risk For visualization >> MATCH (a:RISKSOURCE {Name:"Health and Safety"})-[:hasRisk]->(b:RISK) RETURN a, b
3 | Obtain the risk assessment details of health and safety risks (Risk probability, impact, and rating). | >> MATCH(a:RISKSOURCE{Name:"Health and Safety"})-[:hasRisk]->(n:RISK)-[:hasRiskRating]->(m:RISKRATING) RETURN a.Name AS RiskSource, n.Name AS RiskCode, n.Description AS RiskName, m.Probability As RiskProbability, m.Impact AS RiskImpact,m.Rating AS RiskRating
4 | Obtain all the risk ratings in the database | >> MATCH(m:RISKRATING) RETURN m.Rating AS RiskRating, COUNT(m.Rating) AS Quantity
5 | Determine the consequences and mitigation strategy of the risks rated “Extreme” in the project. | >>MATCH(a:RISKSOURCE)-[:hasRisk]->(b:RISK) MATCH(b)-[:hasRiskRating]->(c:RISKRATING {Rating:"Extreme"}) MATCH(b)-[:hasRiskConsequence]->(d:RISKCONSEQUENCE) MATCH(b)-[:hasRiskMitigation]->(e:RISKMITIGATION) RETURN a.Name AS RiskSource, b.Name AS RiskCode, b.Description AS Risk, c.Rating As RiskRating, d.Description AS RiskConsequence,e.Description AS RiskMitigation

## Risk Source
S/N | RiskSource
1 | Economy | Fig 5 | PROJECT RISK SOURCES
2 | Nature Conservation
3 | Noise and Vibration
4 | Traffic and Transport
5 | Cultural Heritage
6 | Health and Safety
7 | Water Resources
8 | Non-transport infrastructure
9 | Social
10 | Construction Methodology
11 | Coastal Resources
12 | Air
13 | Waste
14 | Land
15 | Climate

## Health&Safety H&S) Risks
Table 3
H&S Risks Visualization
RiskCode | Risk
HS01 | Construction traffic.
HS03 | Construction health and safety.
HS02 | Public health and safety.

## H&S risk assessment
Table 4
Risk Source | Risk Code | Risk Name | Risk Probability | Risk Impact | Risk Rating
Health and Safety | HS01 | Construction traffic. | Likely | Moderate | High
Health and Safety | HS03 | Construction health and safety. | Unlikely | Major | Moderate
Health and Safety | HS02 | Public health and safety. | Unlikely | Major | Moderate

## Risk Rating Counts
RiskRating | Quantity
High | 27
Low | 18
Moderate | 34
Negligible | 13
Extreme | 2

## Risk Conseq. and Mitigation
table 5
Risk Source | Risk Code | Risk | Risk Rating | Risk Consequence | Risk Mitigation
Nature Conservation | NC01 | Sediment destabilization through changes in sediment transport regime (e.g. dredging in adjacent areas). | Extreme | Seagrass impacts | Use of silt curtains during dredging and dredge protocols contained in project EMP.
Nature Conservation | NC06 | Noise pollution (impact on organisms relying on seagrass beds). | Extreme | Seagrass impacts | Visual survey of site to detect noise sensitive species prior to commencement of construction works. Dispersal of noise sensitive species using motorised vessel.
Risk Consequence and Mitigation